# 08-Project Controls S-Curve Module
Example Exam Questions

You can ask exam questions on two levels.  Given a typical set of data, can the student draw the chart and arrive at the answer using the correct procedure?  Given the answer, can the student interpret the results in a simplistic way?  Can the student work the problem backwards, given some of the data and the correct answer?

## Standard Level 2 Problem

Given the following set of planned and actual cost and schedule data (in percents), plot the S-Curves and answer the following questions.

- What is your schedule variance (ahead or behind)?  Express your answer to the nearest tenth of a month.

- What is your cost variance (over or under)?  Express your answer to the nearest dollar.

- What would be your plan for getting back on schedule and budget, if any action is required at all?

About 60% get this problem correct.  I do take off for failure to draw the lines and label the curves, etc. The major problem is plotting the curves correctly.  Students know that I always ask a very similar problem and  there are plenty of old exams floating around.

An Example Level 3 Problem.

An estimate of project status at week 14 reveals that the project is 2 weeks behind schedule and that 55% of the budget has been spent.  Use the Planned S-Curves on the following page to estimate work actually in place.  (Yes, you DO have all the information that you need.  I just asked the problem backwards.)  Then, determine by how much the project is over (or under) budget, based upon the work in place?

Success rate on this problem has been less than 50%.  The standard mistake is to start off backwards – misplace the ending as-built point.

An Example Linear Model Control Program

The plans call for pouring a 120,000 sq-ft floor slab in 6 weeks.  You are the PM for the concrete slab sub-contractor. You have estimated that it will take 1,200 crew hours to complete the work and that your costs are $100 per hour.  At the end of 2 weeks, you make a progress check.  Based upon your figures, you have placed 55,000 sq-ft, and have expended 500 crew-hours.

What is the current project status, in terms of weeks and dollars?

What will be the status of the project when it is complete, in terms of weeks and dollars?

How much faster (slower) should you work (in terms of square-feet per week) to finish exactly on schedule?

Assuming that you adjusted the work rate at the check point, what is the status of the job 1-week later?